## README
Gayini — path to 10 August
Built | 29 July 2026 · 13 days to deadline including today
Deadline | Monday 10 August 2026 — hard. Client deliverables (Nari Nari).
How to use | Tasks sheet is the ranked backlog. Daily_tracker is the plan — one block per day, tick Status as you go. Blockers is what stops what.
Status values | NOT STARTED / IN PROGRESS / DONE / BLOCKED / DROPPED. Set from the dropdown; DONE turns green, BLOCKED turns red.
On the T-numbers | T1-T13 are identifiers, not a sequence. They record the order specs were written, nothing else. Priority is the P-rank column. Do not infer order from the T-number.
Ranking logic | P1 blocks a client deliverable. P2 has a closing window. P3 is high client value and unblocked. P4 is scientific value that can slip. P5 is tidy-up, explicitly after the 10th.
The one dated window | T13 must run BEFORE Ernest's land-use history arrives. It classifies paddock-parts using only cover and water; if the thresholds are fixed before the land-use labels exist, the coincidence test is blind. Afterwards it is contaminated. The window closes when he replies.
Three streams | RS = reference-state analysis (this chat + CC). REP = report stream. BIO = biodiversity repo. Owner column says which.
After the 10th | Tidy-up is explicitly deferred: I-19 test wiring, I-30 lint hardening, PIN 2 revisit, deck v4, T3 build, the full 115-part scan write-up.

## Tasks
Remaining tasks, ranked
P-rank is priority. T-numbers are identifiers only and carry no order.
P | ID | Task | Why it matters | Owner | Effort | Blocks | Target | Status
1 | REG-1 | Register the expectation intercept (52.65) and promote the 64-paddock residual table to a DB object | Report pages 3 and 4 rest on it. Two of five pages of every paddock report cannot ship without it. | RS / CC | 2 h | REP pages 3-4 | 30 Jul | NOT STARTED
2 | REG-2 | Composition view with dominance column, both denominators (focus-3 and all-classes) | The report batch must branch on dominance without re-deriving it. Settles the 14 vs 17 count. | RS / CC | 2 h | REP batch | 30 Jul | NOT STARTED
3 | REP-1 | Switch paddock report page 4 from the five-period trajectory to the annual series | The five-period split has no producing script and is permanently superseded (PIN 3 / I-29). It cannot ship. | REP | 3 h | every paddock report | 30 Jul | NOT STARTED
4 | T14 | Part-grain expectation — fit floor vs flood WITHIN each community across the 115 parts | Makes report page 4 the same grain as page 3. Removes the composition problem by construction rather than adjusting for it. Flood slope drops 0.548 to 0.374 once composition is in the model. | RS / CC | 1 d | REP page 4 correctness | 31 Jul | NOT STARTED
5 | T13 | Paddock-part classification — 115 parts as recovering / persistently poor / declining / unremarkable, with PRE-REGISTERED thresholds | WINDOW CLOSES WHEN ERNEST REPLIES. Blind classification makes the land-use coincidence test clean. Substrate already exists (T10_gateC_percommunity.csv). | RS / CC | 1 d | the Ernest test | 31 Jul | NOT STARTED
6 | PRE-1 | Write down both streams' predictions about Ernest's data, dated, before it arrives | LOOC-B already predicts the always-zero blocks are cleared country. RS predicts Bala 29ca's western parts were cleared. Recording these before the answer is the difference between a test and a story. | RS design seat | 1 h | credibility of the test | 30 Jul | NOT STARTED
7 | T11 | Paddock and paddock-PART maps — floor, flood frequency, and the T10 residual panel | The strongest client-facing artefact available. Maps of which country is recovering, declining or persistently poor. Unblocked: T10 Gate C residuals now exist. | RS / CC | 1 d | report figures, deck | 1 Aug | NOT STARTED
8 | T7 | Persistence surface — recolour emerald-max, overlay paddocks, vectorise to GeoPackage | Unblocked, contrary to earlier advice. The recoloured map and the .gpkg stand alone; only the LiDAR-overlap purpose needs T3. | RS / CC | 1 d | Adrian's LiDAR test | 2 Aug | NOT STARTED
9 | BIO-X1 | Verify Bala 27ca's LOOC-B zero block against RS cover — real, or a product artefact? | LOOC-B says 67.2% hard zero, median 0.000, static 17 years. RS says residual -0.91, the MOST normal reference paddock. If the zero is an artefact it is a significant caveat on the biodiversity deliverable. | RS / CC | 4 h | BIO deck credibility | 1 Aug | NOT STARTED
10 | BIO-X2 | Bala 29ca coincidence test — does the LOOC-B zero block sit on the RS Aeolian/Riverine thirds? | 29.5% zero on condition, 32.3% Aeolian on composition. If they coincide, two independent products locate the same degraded ground. Strongest disturbance evidence available before Ernest. | RS / CC | 4 h | the disturbance story | 2 Aug | NOT STARTED
11 | REP-2 | Parameterise the report builder against the database — literals to queries | The work that turns 2 documents into 77. Nothing else scales. | REP | 2 d | the whole batch | 1 Aug | NOT STARTED
12 | REP-3 | Graceful degradation — Bala 27ca has no sites; single-community paddocks need page 3 to shrink | Run page 3 everywhere and let it degrade to one line. Different page counts invite the reader to wonder what is missing. | REP | 4 h | batch robustness | 1 Aug | NOT STARTED
13 | REP-4 | Build the 4 conserved paddock reports + 21 site reports | STEP 1 of the deliverable. 26ca 3 sites, 27ca 0, 28ca 8, 29ca 10 of 13 after treed exclusion. | REP | 2 d | step 2 | 3 Aug | IN PROGRESS
14 | REP-5 | Build the 60 grazed paddock reports + remaining sites | STEP 2. The bulk of the deliverable. | REP | 3 d | 10 Aug delivery | 7 Aug | NOT STARTED
15 | REP-6 | Register the 9 new report figures in figure_asset | Provenance. Unregistered figures in a client deliverable is the defect this project exists to avoid. | REP / CC | 2 h | provenance | 5 Aug | NOT STARTED
16 | EMAIL-1 | Ernest — was the drier WESTERN part of Bala 29ca cleared or cropped? | Three tasks have converged on this being the decisive input. Costs an email. Still not sent. | Hugh | 15 min | T13 test, BIO 7.1 | 29 Jul | NOT STARTED
17 | EMAIL-2 | Nari Nari — is the unzoned country grazed more, less, or not at all? | Decides between the two readings of the third arm. No computation can settle it. | Hugh | 15 min | T6 interpretation | 29 Jul | NOT STARTED
18 | EMAIL-3 | Stocking rates / DSE per hectare | Whether 14-day and standard grazing differ in intensity at all. | Hugh | 15 min | grazing framing | 29 Jul | NOT STARTED
19 | BIO-1 | Run RS_export_layers_for_biodiversity — the guarded cross-repo export | Task N is stopped at Gate 0 until this lands. The sandbox run bypassed it by reading file copies. | RS / CC | 4 h | BIO Task N | 3 Aug | NOT STARTED
20 | BIO-2 | Task N build — condition x inundation, verification against the sandbox expected values | Turns the §7 amendment numbers into registered results. Gates are verification, not discovery. | BIO / CC | 2 d | BIO deck | 6 Aug | NOT STARTED
21 | RECON-1 | Reconcile the LOOC-B 40% threshold against the RS linear floor-flood relationship | LOOC-B: condition is a step at ~40% flood frequency. RS: floor is linear at +0.548/pp. Both may be true, but they imply different management advice and both decks will say what water does. | RS design seat | 4 h | both decks | 5 Aug | NOT STARTED
22 | DECK-1 | Rebuild the reference-state deck v4 with the pinned numbers and the new maps | Ten numbers changed under the pins. Review deck for Adrian, not the client deliverable. | RS design seat | 1 d | Adrian review | 7 Aug | NOT STARTED
23 | QA-1 | Run test_T8_headline_reproduction.py before EVERY report batch | 56 pinned numbers re-derived by an independent path. Exits non-zero on drift. Not in the smoke test (I-19), so it must be run explicitly. The only thing between a stale number and 77 documents. | REP + RS | 5 min | every batch | every batch | NOT STARTED
24 | T3 | Build the refugia / always-green surface | Specified, never built. T7's LiDAR-overlap purpose needs it. AFTER THE 10TH unless everything else lands. | RS / CC | 1 d | T7 full purpose | after 10 Aug | NOT STARTED
25 | TIDY-1 | I-19 test wiring, I-30 lint hardening, PIN 2 revisit, L-01 into the methods doc | Known-unprotected surfaces and one weak pin decision. Explicitly deferred. | RS / CC | 1 d | nothing | after 10 Aug | NOT STARTED

## Daily_tracker
Day by day to 10 August
One row per day. Fill Done / Slipped / Notes as you go. Sunday 9 Aug is contingency by design — keep it empty.
Day | Plan | Task IDs | Done? | Slipped to | Notes
Wed 29 Jul | SEND THE THREE EMAILS (EMAIL-1/2/3). Write the prediction record (PRE-1). Kick CC on REG-1 and REG-2. | EMAIL-1, EMAIL-2, EMAIL-3, PRE-1
Thu 30 Jul | REG-1 and REG-2 land. REP-1 page-4 switch. Start T14 part-grain expectation. | REG-1, REG-2, REP-1
Fri 31 Jul | T14 completes. T13 spec written and run with pre-registered thresholds. | T14, T13
Sat 1 Aug | T11 maps. BIO-X1 Bala 27ca verification. REP-2 parameterisation starts. | T11, BIO-X1
Sun 2 Aug | T7 persistence map + GeoPackage. BIO-X2 coincidence test. | T7, BIO-X2
Mon 3 Aug | REP-4 step 1 batch: 4 conserved paddocks + 21 sites. BIO-1 export. | REP-4, BIO-1
Tue 4 Aug | Step 1 review and fixes. REP-3 degradation paths proven on 27ca. | REP-3
Wed 5 Aug | REP-6 figure registration. RECON-1 threshold reconciliation. | REP-6, RECON-1
Thu 6 Aug | BIO-2 Task N build. Step 2 batch begins. | BIO-2
Fri 7 Aug | REP-5 grazed paddock batch. DECK-1 rebuild. | REP-5, DECK-1
Sat 8 Aug | Batch completion. Full QA-1 reproduction run across everything. | QA-1
Sun 9 Aug | Contingency. Nothing new starts today — this day exists to absorb slippage.
Mon 10 Aug | DELIVER. Final QA-1 run before anything leaves. | DELIVERY

## Blockers
What stops what
Ordered by consequence, not by date.
Blocker | Blocks | Owner | Note
REG-1 | REP pages 3-4 of every paddock report | RS / CC | Two of five pages cannot ship. Highest-consequence dependency on the board.
REG-2 | REP batch branching on dominance | RS / CC | Without it the batch re-derives composition, and two streams deriving the same number differently is how this project got a provenance audit.
REP-1 | every paddock report | REP | The five-period trajectory has NO producing script and is permanently superseded. Not a registration gap — a defect.
Ernest's reply | T13's blind window | external | T13 must be RUN BEFORE the reply arrives, not after. This is the only dependency that gets worse with time.
BIO-1 export | BIO Task N Gate 0 | RS / CC | Task N is stopped until the guarded export lands.
T3 | T7's stated LiDAR-overlap purpose | RS / CC | T7's map and GeoPackage do NOT need T3 — only the refugia comparison does. Do not let this block T7.